## HA Test Scenarios
TC ID | Scenario | Objective | Priority | Preconditions | Step No | Action (exact command / operation) | Expected Result | Pass/Fail | Actual Result / Evidence | Notes
TC-001 | Initial Connection to PRIMARY | Verify the Spring Boot HAClient establishes its initial connection to PRIMARY and creates all four queue subscriptions correctly. | High | amps-config-primary.xml and amps-config-secondary.xml deployed; ports 9007/9017/8085/8185 free on 172.21.12.69; application.yaml has both HAClient URIs configured. | 1 | Start PRIMARY: /home/shan/app-env/scripts/start-primary.sh | Process starts; amps.log shows: "Instance 'amps-queue-concurrency-primary' started, listening on tcp://0.0.0.0:9007"
[5 empty] | 2 | Verify PRIMARY admin UI: curl -s -o /dev/null -w "%{http_code}\n" http://172.21.12.69:8085 | HTTP 200 returned
[5 empty] | 3 | Start SECONDARY: /home/shan/app-env/scripts/start-secondary.sh | Process starts cleanly on 9017; no port-conflict errors with PRIMARY
[5 empty] | 4 | Verify SECONDARY admin UI: curl -s -o /dev/null -w "%{http_code}\n" http://172.21.12.69:8185 | HTTP 200 returned
[5 empty] | 5 | Start the Spring Boot application (jar or mvn spring-boot:run) | Application context starts with no exceptions; ampsHaClient bean initializes
[5 empty] | 6 | Inspect application log for the connection line | Log shows: "Connected to tcp://172.21.12.69:9007"
[5 empty] | 7 | Inspect application log for logon confirmation | Log shows: "Logon successful, client name=trades-service"
[5 empty] | 8 | Inspect application log for all four subscriptions | Log shows "Subscription established: queue=/queue/trades" and equivalents for /queue/orders, /queue/risk, /queue/test-trades
[5 empty] | 9 | Open PRIMARY admin UI (8085) -> Connected Clients panel | Client "trades-service" listed, with 4 active subscriptions shown
TC-002 | Primary Failure -> Failover to Secondary | Verify the HAClient detects PRIMARY going down, reconnects to SECONDARY, and resubscribes automatically with zero application restart. | High | TC-001 passed; both servers running; app connected to PRIMARY with all 4 subscriptions active. | 1 | Publish 5 test messages to /queue/trades via a test publisher | All 5 accepted (ACK'd); subscriber log shows 5 receives on PRIMARY
[5 empty] | 2 | Note PRIMARY's PID: pgrep -fal amps-config-primary.xml | PID captured for reference in TC-003
[5 empty] | 3 | Stop PRIMARY: /home/shan/app-env/scripts/stop-primary.sh | Process terminates; port 9007 refuses new connections
[5 empty] | 4 | Observe application log within 5s of stopping PRIMARY | Log shows: "WARN Connection lost: tcp://172.21.12.69:9007"
[5 empty] | 5 | Observe reconnect attempts in application log | Log shows increasing backoff: "Attempting reconnect (attempt 1, delay=200ms)", then attempt 2 at 400ms, etc.
[5 empty] | 6 | Wait for reconnect to complete (should be within a few seconds given ExponentialDelayStrategy ceiling of 5000ms) | Log shows: "INFO Connected to tcp://172.21.12.69:9017"
[5 empty] | 7 | Observe resubscribe sequence | Log shows "Resubscribing existing subscriptions" followed by "Subscription successful: queue=/queue/trades (resumed from bookmark=N)" for all 4 queues
[5 empty] | 8 | Publish 3 more messages to /queue/trades | All 3 received by the subscriber via SECONDARY with no manual intervention
[5 empty] | 9 | Open SECONDARY admin UI (8185) -> Connected Clients panel | Client "trades-service" listed with 4 active subscriptions
TC-003 | Primary Recovery / Failback Policy | Verify correct, documented behavior when PRIMARY returns while the client is on SECONDARY: confirm whether the client stays or fails back per the ServerChooser policy. | High | TC-002 completed; client currently connected to SECONDARY. | 1 | Start PRIMARY: /home/shan/app-env/scripts/start-primary.sh | PRIMARY comes up clean; port 9007 listening; admin UI 8085 returns 200
[5 empty] | 2 | Wait 15s, observe application log | DefaultServerChooser does NOT proactively migrate off a healthy connection; client remains on SECONDARY (9017) — confirm this matches intended design
[5 empty] | 3 | Stop SECONDARY: /home/shan/app-env/scripts/stop-secondary.sh | Log shows: "Connection lost: tcp://172.21.12.69:9017"
[5 empty] | 4 | Observe reconnect wraps to next chooser entry | Log shows: "Connected to tcp://172.21.12.69:9007" (back on PRIMARY)
[5 empty] | 5 | Observe resubscribe on PRIMARY | Log shows "Subscription successful: queue=/queue/trades (resumed from bookmark=N)"; note any bookmark gap if messages were only ever sent to SECONDARY (no replication configured)
[5 empty] | 6 | Restart SECONDARY for subsequent tests: /home/shan/app-env/scripts/start-secondary.sh | SECONDARY available again; admin UI 8185 returns 200
TC-004 | Secondary Failure While on PRIMARY | Confirm SECONDARY being down has zero observable impact while the client is actively and stably connected to PRIMARY. | Medium | App connected and stable on PRIMARY (9007); SECONDARY running. | 1 | Confirm current connection target via app log / PRIMARY admin UI | Client shown connected to PRIMARY (9007)
[5 empty] | 2 | Stop SECONDARY: /home/shan/app-env/scripts/stop-secondary.sh | SECONDARY log shows clean shutdown; PRIMARY log shows no related entries
[5 empty] | 3 | Publish 5 messages to /queue/orders | All 5 processed normally; zero WARN/ERROR lines in application log
[5 empty] | 4 | Continuously consume from /queue/risk for 30s | No reconnect attempts logged; steady-state consumption, no interruption
[5 empty] | 5 | Restart SECONDARY: /home/shan/app-env/scripts/start-secondary.sh | SECONDARY returns to service with no effect on the already-stable PRIMARY connection
TC-005 | Both Servers Down -> Retry Loop | Verify the app retries indefinitely (maxRetryCount=-1) and self-heals the moment either server becomes reachable again, with no manual app restart. | High | App running and connected (either node). | 1 | Stop PRIMARY: /home/shan/app-env/scripts/stop-primary.sh | Connection-lost detected; reconnect attempts begin toward SECONDARY
[5 empty] | 2 | Immediately stop SECONDARY too: /home/shan/app-env/scripts/stop-secondary.sh (before failover completes) | Reconnect attempt to SECONDARY also fails; log shows repeated WARN reconnect attempts cycling PRIMARY -> SECONDARY -> PRIMARY with backoff capped at 5000ms
[5 empty] | 3 | Let the retry loop run for 60s | No unhandled exception, no app crash; process stays alive; CPU stays low (confirms backoff, not a busy-loop)
[5 empty] | 4 | Start SECONDARY only: /home/shan/app-env/scripts/start-secondary.sh | Within one backoff cycle (<=5s) log shows "Connected to tcp://172.21.12.69:9017" and successful resubscribe
[5 empty] | 5 | Start PRIMARY: /home/shan/app-env/scripts/start-primary.sh | PRIMARY reachable; record actual observed chooser behavior (stays on SECONDARY vs. fails back)
TC-006 | Repeated Failover Stability / Resource Leak Check | Verify no memory, thread, or subscription leak accumulates across repeated failover cycles. | Medium | App running; Spring Actuator metrics endpoints enabled. | 1 | Record baseline via GET /actuator/metrics/jvm.memory.used and /actuator/metrics/jvm.threads.live | Baseline heap usage and live thread count recorded
[5 empty] | 2 | Cycle: stop-primary.sh, wait 5s, start-primary.sh, wait 5s -- repeat 5 times | Each cycle logs a successful reconnect + resubscribe sequence; no errors
[5 empty] | 3 | Cycle: stop-secondary.sh, wait 5s, start-secondary.sh, wait 5s -- repeat 5 times | Same as above for SECONDARY-side cycling
[5 empty] | 4 | Re-check jvm.memory.used and jvm.threads.live after 10 total cycles | Values within ~10% of baseline; no unbounded growth, no orphaned reconnect threads
[5 empty] | 5 | Confirm subscription count via admin UI on whichever node is currently active | Exactly 4 active subscriptions (not 8+), confirming old subscriptions are torn down each reconnect rather than stacking
TC-007 | Resubscribe Verification Per Queue | Confirm all four queues resubscribe correctly and independently after failover, not just /queue/trades. | High | App connected to PRIMARY, subscribed to all 4 queues. | 1 | Stop PRIMARY: /home/shan/app-env/scripts/stop-primary.sh | Connection-lost detected
[5 empty] | 2 | Wait for reconnect to SECONDARY | Log shows: "Connected to tcp://172.21.12.69:9017"
[5 empty] | 3 | Check log for /queue/trades resubscribe | "Subscription successful: queue=/queue/trades"
[5 empty] | 4 | Check log for /queue/orders resubscribe | "Subscription successful: queue=/queue/orders"
[5 empty] | 5 | Check log for /queue/risk resubscribe | "Subscription successful: queue=/queue/risk"
[5 empty] | 6 | Check log for /queue/test-trades resubscribe | "Subscription successful: queue=/queue/test-trades"
[5 empty] | 7 | Publish one message to each of the 4 queues | Subscriber receives all 4 messages via SECONDARY
TC-008 | Publisher Recovery / Delivery During Failover | Verify publishes issued during the reconnect window are queued (PublishStore) and flushed, not silently dropped. | High | MemoryPublishStore configured on the HAClient; app connected to PRIMARY. | 1 | Stop PRIMARY: /home/shan/app-env/scripts/stop-primary.sh | Connection-lost detected
[5 empty] | 2 | Immediately call client.publish("/queue/trades", ...) 3 times from a test thread, before SECONDARY connect completes | Publish calls return without throwing; HAClient buffers them in the PublishStore
[5 empty] | 3 | Wait for reconnect to SECONDARY to complete | Log shows: "Connected to tcp://172.21.12.69:9017"
[5 empty] | 4 | Verify all 3 buffered publishes are flushed | SECONDARY admin UI / subscriber confirms all 3 messages delivered; none lost
[5 empty] | 5 | Compare publish timestamps vs. delivery timestamps | Delivery occurs shortly after reconnect, confirming store-and-forward rather than silent drop
TC-009 | Subscriber Idempotency / Duplicate Handling | Confirm subscriber logic tolerates possible duplicate delivery across a failover boundary (at-least-once semantics). | High | Subscriber handler implements dedupe-by-id logic per the setup guide's HAClient chapter. | 1 | Publish a message with id=9001 to /queue/trades | Received once, processed once
[5 empty] | 2 | Stop PRIMARY mid-lease, before the consumer's ack completes, to force possible redelivery | Message becomes eligible for redelivery once LeaseTimeout (5000ms) elapses on whichever node re-serves it
[5 empty] | 3 | Observe subscriber logs for id=9001 | If redelivered, subscriber logs "duplicate id=9001 ignored" rather than double-processing it
[5 empty] | 4 | Verify downstream state (DB/cache) for id=9001 | Exactly one applied update recorded, despite possible duplicate delivery at the transport layer
TC-010 | Admin UI Cross-Check | Confirm both Admin UIs independently reflect accurate, real-time, and non-shared state. | Low | Both PRIMARY and SECONDARY running. | 1 | Open http://172.21.12.69:8085 (PRIMARY admin) | Dashboard loads; instance name shown as "amps-queue-concurrency-primary"
[5 empty] | 2 | Open http://172.21.12.69:8185 (SECONDARY admin) | Dashboard loads; instance name shown as "amps-queue-concurrency-secondary"
[5 empty] | 3 | Check queue depth for /queue/trades on PRIMARY | Matches the expected message backlog count for the current test state
[5 empty] | 4 | Check queue depth for /queue/trades on SECONDARY | Independent value (0 if no replication configured), confirming no shared state between instances
[5 empty] | 5 | Check Connected Clients panel on whichever node the app is currently attached to | Exactly one entry for "trades-service"
TC-011 | Lease Timeout / Redelivery Behavior | Verify a message whose consumer never acks is redelivered after LeaseTimeout expires, and is not stuck indefinitely. | Medium | PRIMARY running; a test consumer configured to intentionally never ack. | 1 | Publish message id=1234 to /queue/test-trades | Delivered to the test consumer; consumer intentionally withholds ack
[5 empty] | 2 | Wait 1500ms (< 2000ms LeaseTimeout configured for test-trades) | Message remains leased to the original consumer; not yet redelivered
[5 empty] | 3 | Wait until total elapsed time exceeds 2000ms | Lease expires; message becomes eligible for redelivery
[5 empty] | 4 | Have a second consumer poll /queue/test-trades | Message id=1234 is redelivered to the second consumer
[5 empty] | 5 | Confirm the original consumer's stale lease does not cause a stuck duplicate delivery | Only one active lease exists at a time; admin UI queue view shows no orphaned lease entries
TC-012 | Bookmark Resume Validation | Confirm the bookmark store correctly tracks position so a resubscribe resumes rather than replaying from scratch or skipping messages. | High | Durable/tracked bookmark subscription in place (MemoryBookmarkStore, or a persistent store for the restart step). | 1 | Publish messages 1-10 to /queue/orders; consumer processes all 10 | Bookmark advances to 10; logged accordingly
[5 empty] | 2 | Stop PRIMARY: /home/shan/app-env/scripts/stop-primary.sh | Reconnect to SECONDARY; resubscribe log shows "resumed from bookmark=10"
[5 empty] | 3 | Publish messages 11-15 | Consumer receives exactly messages 11-15 (5 messages) -- no replay of 1-10, no gap
[5 empty] | 4 | Kill the app JVM (kill -9) and restart it, using a persistent bookmark store | On restart, consumer resumes from bookmark=15; does not reprocess 1-15
TC-013 | Simulated Network Partition vs. Process Stop | Distinguish process-kill failover (TC-002) from a network-level partition, since silent packet loss can behave differently for detection timing than a clean TCP FIN. | Medium | Ability to block traffic via firewall rule (iptables in WSL, or a comparable network-level block). | 1 | Block outbound traffic to 172.21.12.69:9007: sudo iptables -A OUTPUT -p tcp --dport 9007 -j DROP | PRIMARY process keeps running server-side; app can no longer reach it
[5 empty] | 2 | Observe application log | No clean FIN is received; detection relies on TCP timeout rather than an immediate "Connection lost" -- record the actual detection delay, expect it to be longer than TC-002's
[5 empty] | 3 | Once detected, verify reconnect to SECONDARY proceeds | Same reconnect/resubscribe log sequence as TC-002, just at a later timestamp
[5 empty] | 4 | Remove the block: sudo iptables -D OUTPUT -p tcp --dport 9007 -j DROP | PRIMARY reachable again; confirm the firewall rule was fully removed, no leftover block
TC-014 | Concurrent Multi-Threaded Publisher Load During Failover | Validate the HAClient handles failover correctly under concurrent publish load from multiple threads -- directly relevant given this AMPS instance is named amps-queue-concurrency. | High | Load-test harness configured: e.g. 10 threads each publishing continuously to /queue/trades. | 1 | Start 10 publisher threads at ~50 msgs/sec each (500 msgs/sec aggregate) | Steady-state publishing for a 30s baseline with zero errors
[5 empty] | 2 | Stop PRIMARY mid-load: /home/shan/app-env/scripts/stop-primary.sh | Brief spike in publish latency / buffered-but-not-yet-sent count during the reconnect window; no thread deadlocks; no OutOfMemoryError from unbounded PublishStore growth
[5 empty] | 3 | Observe reconnect completes | All 10 threads resume publishing to SECONDARY without any individual thread restart
[5 empty] | 4 | Tally total messages published vs. total received on SECONDARY's /queue/trades after the test ends | Received count matches published count (allowing for legitimate at-least-once duplicates, but zero losses)
TC-015 | Disk-Usage Failsafe Action | Verify the amps-action-do-shutdown disk-usage guard actually fires and is distinguishable in logs from an unplanned crash. | Medium | Ability to simulate high disk usage on the volume backing /home/shan/app-env/data/amps (dummy file, or a small dedicated test volume). | 1 | Fill the PRIMARY data volume to >95% usage with a dummy file | Within one 10s check cycle, PRIMARY log shows: "CRITICAL: Shutting down AMPS (PRIMARY) due to lack of disk space"
[5 empty] | 2 | Confirm PRIMARY process actually exits: pgrep -fal amps-config-primary.xml | No process returned
[5 empty] | 3 | Confirm the app fails over to SECONDARY exactly as in TC-002 | Same reconnect/resubscribe sequence -- confirms the disk-guard shutdown is operationally indistinguishable from any other PRIMARY-down scenario, from the client's perspective
[5 empty] | 4 | Remove the dummy file, restart PRIMARY | PRIMARY starts cleanly once usage drops back under 95%
TC-016 | Config Drift Check -- LeaseTimeout Sync | Regression-guard against amps.queue.lease-timeout-ms in application.yaml silently diverging from <LeaseTimeout> in either AMPS config. | Low | Read access to amps-config-primary.xml, amps-config-secondary.xml, and application.yaml. | 1 | Extract <LeaseTimeout> per queue from amps-config-primary.xml | 5000 for trades/orders/risk; 2000 for test-trades
[5 empty] | 2 | Extract the same values from amps-config-secondary.xml | Identical to PRIMARY's values for every queue
[5 empty] | 3 | Extract amps.queue.lease-timeout-ms from application.yaml | 5000 -- matches the primary-queue lease value the app expects
[5 empty] | 4 | Flag as FAIL if any of the three sources disagree | Recommend wiring this as an automated diff step in CI/release checklist rather than a one-time manual check

## Test Case Summary
TC ID | Scenario | Priority | Objective | Overall Expected Outcome | Status | Executed By | Date Executed
TC-001 | Initial Connection to PRIMARY | High | Verify the Spring Boot HAClient establishes its initial connection to PRIMARY and creates all four queue subscriptions correctly. | Final step: Client "trades-service" listed, with 4 active subscriptions shown
TC-002 | Primary Failure -> Failover to Secondary | High | Verify the HAClient detects PRIMARY going down, reconnects to SECONDARY, and resubscribes automatically with zero application restart. | Final step: Client "trades-service" listed with 4 active subscriptions
TC-003 | Primary Recovery / Failback Policy | High | Verify correct, documented behavior when PRIMARY returns while the client is on SECONDARY: confirm whether the client stays or fails back per the ServerChooser policy. | Final step: SECONDARY available again; admin UI 8185 returns 200
TC-004 | Secondary Failure While on PRIMARY | Medium | Confirm SECONDARY being down has zero observable impact while the client is actively and stably connected to PRIMARY. | Final step: SECONDARY returns to service with no effect on the already-stable PRIMARY connection
TC-005 | Both Servers Down -> Retry Loop | High | Verify the app retries indefinitely (maxRetryCount=-1) and self-heals the moment either server becomes reachable again, with no manual app restart. | Final step: PRIMARY reachable; record actual observed chooser behavior (stays on SECONDARY vs. fails back)
TC-006 | Repeated Failover Stability / Resource Leak Check | Medium | Verify no memory, thread, or subscription leak accumulates across repeated failover cycles. | Final step: Exactly 4 active subscriptions (not 8+), confirming old subscriptions are torn down each reconnect rather than stacking
TC-007 | Resubscribe Verification Per Queue | High | Confirm all four queues resubscribe correctly and independently after failover, not just /queue/trades. | Final step: Subscriber receives all 4 messages via SECONDARY
TC-008 | Publisher Recovery / Delivery During Failover | High | Verify publishes issued during the reconnect window are queued (PublishStore) and flushed, not silently dropped. | Final step: Delivery occurs shortly after reconnect, confirming store-and-forward rather than silent drop
TC-009 | Subscriber Idempotency / Duplicate Handling | High | Confirm subscriber logic tolerates possible duplicate delivery across a failover boundary (at-least-once semantics). | Final step: Exactly one applied update recorded, despite possible duplicate delivery at the transport layer
TC-010 | Admin UI Cross-Check | Low | Confirm both Admin UIs independently reflect accurate, real-time, and non-shared state. | Final step: Exactly one entry for "trades-service"
TC-011 | Lease Timeout / Redelivery Behavior | Medium | Verify a message whose consumer never acks is redelivered after LeaseTimeout expires, and is not stuck indefinitely. | Final step: Only one active lease exists at a time; admin UI queue view shows no orphaned lease entries
TC-012 | Bookmark Resume Validation | High | Confirm the bookmark store correctly tracks position so a resubscribe resumes rather than replaying from scratch or skipping messages. | Final step: On restart, consumer resumes from bookmark=15; does not reprocess 1-15
TC-013 | Simulated Network Partition vs. Process Stop | Medium | Distinguish process-kill failover (TC-002) from a network-level partition, since silent packet loss can behave differently for detection timing than a clean TCP FIN. | Final step: PRIMARY reachable again; confirm the firewall rule was fully removed, no leftover block
TC-014 | Concurrent Multi-Threaded Publisher Load During Failover | High | Validate the HAClient handles failover correctly under concurrent publish load from multiple threads -- directly relevant given this AMPS instance is named amps-queue-concurrency. | Final step: Received count matches published count (allowing for legitimate at-least-once duplicates, but zero losses)
TC-015 | Disk-Usage Failsafe Action | Medium | Verify the amps-action-do-shutdown disk-usage guard actually fires and is distinguishable in logs from an unplanned crash. | Final step: PRIMARY starts cleanly once usage drops back under 95%
TC-016 | Config Drift Check -- LeaseTimeout Sync | Low | Regression-guard against amps.queue.lease-timeout-ms in application.yaml silently diverging from <LeaseTimeout> in either AMPS config. | Final step: Recommend wiring this as an automated diff step in CI/release checklist rather than a one-time manual check
Dashboard
Total Test Cases | 16
Passed | 0
Failed | 0
Blocked | 0
Not Run | 16
Pass Rate | 0%

## Environment
Item | Value
Server host | 172.21.12.69
Shared AMPS binary | /home/shan/amps-5.3.5/bin/amps
PRIMARY config | /home/shan/amps-5.3.5/config/amps-config-primary.xml
SECONDARY config | /home/shan/amps-5.3.5/config/amps-config-secondary.xml
PRIMARY data root | /home/shan/app-env/data/amps
SECONDARY data root | /home/shan/app-env/data/amps-secondary
PRIMARY TCP (tcp-json) | 9007
SECONDARY TCP (tcp-json) | 9017
PRIMARY WebSocket (websocket-any) | 9008
SECONDARY WebSocket (websocket-any) | 9018
PRIMARY Admin UI | 8085
SECONDARY Admin UI | 8185
Queues under test | /queue/trades, /queue/orders, /queue/risk, /queue/test-trades
LeaseTimeout (trades/orders/risk) | 5000 ms
LeaseTimeout (test-trades) | 2000 ms
HAClient endpoints (ordered) | tcp://172.21.12.69:9007/amps/json ; tcp://172.21.12.69:9017/amps/json
Reconnect strategy | ExponentialDelayStrategy: initial=200ms, max=5000ms, retries=unlimited
Resubscribe after reconnect | true
Bookmark store | MemoryBookmarkStore (lab) / persistent store (recommended for TC-012 restart step)
Publish store | MemoryPublishStore
Start scripts | /home/shan/app-env/scripts/start-primary.sh ; start-secondary.sh
Stop scripts | /home/shan/app-env/scripts/stop-primary.sh ; stop-secondary.sh
Log files | /home/shan/app-env/data/amps/logs/amps.log ; /home/shan/app-env/data/amps-secondary/logs/amps.log

## Legend
How to use this workbook
1. "HA Test Scenarios" is the execution sheet — one row per step. Fill in Pass/Fail (dropdown) and Actual Result/Evidence as you go.
2. "Test Case Summary" is the roll-up sheet for a test-run report — one row per test case, plus a Dashboard with live Pass/Fail counts (formulas, recalculates automatically).
3. "Environment" records the exact hosts, ports, paths, and HAClient settings this run was executed against — attach this sheet to any bug report so failures are reproducible.
4. Priority: High = must pass before sign-off; Medium = should pass, file a ticket if not; Low = nice-to-have coverage / hygiene checks.
5. Status values: Pass, Fail, Blocked (couldn't execute — e.g. environment unavailable), Not Run.
6. TC-013 through TC-016 require extra setup (iptables access, a disk-fillable test volume, a load-test harness, or file access) — schedule these separately from the core TC-001..TC-012 smoke pass.